Title
Schedule
Murrough Landon
19 April 2007
A brief update of Bruces talk at Mainz
External Links
Calorimeter Signals
Internal Tests
System Tests
Combined Runs
Schedule

---
External Links
CMM-CTP: need to retest repaired cables and new CMM firmware
  - Week of 23 May is best overlap between us and Ralf
RoIB: try tests with combined partition?
ROS: move to final ROS instead of mobile ROS?
  - Also produce final databases including the final ROSes

---
Calorimeter Signals
Signal integrity tests for TileCal Barrel C side, all TileCal ext. barrel and all LAr still to be done
  - Easiest with VME readout until we have more RODs
    - And have the ROD/GNAM/COOL software!
With ROD readout SW, need to do more detailed scans with calorimeters than possible via VME
  - Still quite a bit of SW work
    - Presently some intractable problems with GNAM & COOL
Scheduling requires coordination with LAr and Tile
  - Who both have busy schedules and their own problems

---
Internal (Subsystem) Tests
Need development and testing of PPM readout
  - PPM firmware changes
Further checking of PPM-JEM LVDS in FCAL region
Full crate tests of both CP and JEP systems with fully working backplanes
  - To check for more subtle problems
  - Still awaiting more CMMs and CMM-RTMs

---
System Tests
When can we connect up some LVDS cables?
  - Should have one good crate (in jep1 position?) at the end of this week, together with four good PP crates on the A side
  - Cable discharge kit available next week?
  - How many cables to connect and when?
    - Ideally start cabling from left hand end of crates (as view from the back) and cable complete slots (CP + JEP cables)
    - We might like to see real barrel calo signals, so we would need to cable at least half the jep1 crate, to perhaps a quarter of either Tile or LAr A side barrel crates (or both)
We can then start to run some tests of more than just a slice through the system

---
Combined Runs
So far we have only run standalone partitions
We would ideally like to join the June combined run
  - Is this too ambitious?
As preparation we should make some binary integrated runs with some of the following:
  - CTP, RoIB, Tile, LAr
Work required in preparing databases and doubtless much work getting the combined partition going...
  - To join the June “M3” exercise we would need to do all this in the next month (along with everything else in this talk)

---
Critical Items (a small selection)
When do we get more RODs?!?
  - Ditto the CMM (and RTM) production, not to mention the rest of the TCMs, VMMs, etc
Timescale for CP/JEP backplane repairs?
Calibration software, GNAM and COOL database
Monitoring of our event data
Completing the DCS setup (TCM branch)
TDAQ databases for our full system (including cables) for use in combined running
Unknown timescale (and unknown problems) for our full system integration and commissioning

---
Schedule
16 April	Cabling/PPr signals
23 April	CP/DCS, some JEP(?), but not PPr SW?
30 April	JEP?
7 May
14 May	CMM-CTP?
21 May	Cabling
28 May
4 June	Cabling
11 June	Cabling
18 June
25 June	Stockholm Meeting