Title
Cabling Status
Murrough Landon
28 June 2007
Nearly the end of a long story...
Overview
Analogue cables
LVDS cables
Glink fibres
Remaining work

---
Overview

---
Analogue Cables
Almost all short analogue cables are now installed
Remaining are 80 lower C side RPPP cables
  - About 2 or 3 days work, considered low priority
About 40 connectors needed minor repairs
  - Open connector, broken glue
  - These should be retested using the Saclay tester in USA15
    - Need extension cables?
Alain Le Coguie still has all the test results
  - He plans to write a tool to parse his files and enter the results in a database, both for LAr and our cables
    - Tricky as many test files are misnamed
Connectivity tests still required for almost all cables!
  - Only 32 of 776 checked properly with calo pulses

---
Analogue Cables: First Full PPM Rack

---
LVDS Cables (1)
All LVDS cable bundles installed, including spares
  - 1888 cables plus 100 spares in about 200 bundles
    - Many thanks to large number of helpers
Both JEP crates and 2 of 4 CP crates connected
  - Lot of work tidying the cable bundles so the power supplies and back doors can be closed
Three (of 8) PP crates connected (A side)
Still to be done:
  - middle two CP crates, one A side & four C side PP crates
  - comprehensive testing (needs full PP and CP crates)

---
LVDS Cables (2)
Small fraction of LVDS cables now tested
  - Four JEMs and two CPMs fed from eight PPMs
    - 68 out of 1888 LVDS cable assemblies
  - Only basic connection tests (no check for swaps)
One error so far
  - four cables displaced upwards by one row of pins
  - top of CPM slot so easiest to correct

---
LVDS Cables: Before and After

---
LVDS Cables: First Few Connections

---
LVDS Cables: First Complete Crate

---
LVDS Cables: Beautifully Tidy!

---
Glink Fibres
Need 124 fibres, under the floor, from PP crates
  - Separate lengths for C, A sides
  - Ordered, not yet delivered
Need 200 fibres from CP and JEP crates
  - Across the front of the racks
  - Large number of separate precise lengths (to 10cm)
  - Ordered (a bit later), not yet delivered
Requested protective wrapping from R. Mclaren
Aim to install late July or early August

---
Summary of Remaining Work
Install last 80 RPPP cables: half a cabling week
Connect last two CP crates: half a cabling week
Test repaired analogue cables: half a week?
  - Connectors on TCPP cables not yet checked?
Connect remaining five PP crates: two weeks?
  - Paul and Klaus according to their own schedule...
Install underfloor glink fibres: one day?
One further cabling week planned: 9 July
  - Might need one more week?
Also need to install muon terminators at TCPPs
  - Except for channels used for TileCal cosmic trigger

---
Caveat
Few of the installed cables have been tested
  - Neither analogue nor LVDS cables
Any bad LVDS cables will be hard to reconnect
  - Very fiddly and hard to access
Ditto any miscablings in the analogue system
  - Cables cut to “correct” length
Any problems could mean a lot more work!